Newton St Cyres Parish Council

Action /Development Plan – May 2017 to April 2020

Newton St Cyres Parish Council will seek to develop, improve and maintain village services and facilities to the best of its ability within its budget and will have regard to the safety and interests of parishioners as a primary consideration in all council activities.  It will aim to represent parishioner’s views at a local, district and county level.

| Objective | Action | Who is responsible for action? | Timescale | Achieved? |
| --- | --- | --- | --- | --- |
| Implementation of Parish Plan actions | Appointed councillors to continue to work with Development Group and parish organisations to implement actions | Councillors and Development Group | End of April 2018 | Yes |
| To secure land for a new graveyard | To sign legal agreements To apply for grants to fence the land 2017/18 budget includes provision for fencing and solicitor fees | Councillors and Clerk | End of April 2018 | Yes |
| To set up new graveyard | To develop rules, regulations, agree fees etc | Councillors and Clerk | End of April 2019 |  |
| To consider a ANPR camera | Cost and feasibility study to be undertaken 2017/18 budget includes provision for installation | Councillors and Clerk | End of April 2018 | Not feasible so delete from list |
| To investigate a footpath from the new school site to the Rec Ground | Cost and feasibility study to be undertaken Investigate if eligible for S106 | Councillors and Clerk | S106 eligibility check – July 2017 | Not eligible for S106 |
| To investigate Devon County Councils Road Warden Scheme | To consider new information and to decide if to join the scheme or not | Councillors and Clerk | End of December 2018 | Advertising for volunteers |
| To maintain and improve parish footpaths as part of Devon County Council’s (DCC) Parish Partnership Scheme | To report any work required to Footpath Warden | Councillors and Parishioners to report work required to footpath warden who will contact DCC for support if required | Ongoing | Ongoing |
| To consider ways of reducing dog mess | Consider working with parishioners, village organisations | Clerk and councillors | Ongoing |  |

| Objective | Action | Who is responsible for action? | Timescale | Achieved? |
| --- | --- | --- | --- | --- |
| To ensure continued compliance with the relevant current legislation and to promote openness, transparency and community engagement through the use of various communication media. | Clerk to ensure compliance is maintained through website and Facebook page. Councillors to maintain monthly surgeries, Annual report and Directory and two newsletters per year to be produced. Ensure budget includes provision for printing costs | Clerk and councillors | Ongoing |  |
| To maintain an allotment when demanded by 6 parishioners and /or if there are sufficient allotment holders within 3 miles of parish boundary | To ensure the allotments remain financially viable. Ensure they are kept clean and tidy so that new tenants can be attracted | Appointed Councillor and Clerk | Ongoing |  |
| To monitor and review the arboretum | To continue to work with the arboretum committee to ensure continued compliance with the terms of the arboretum licence. To include annual risk assessment | Appointed councillor | Ongoing with annual risk assessment |  |
| To ensure that all council assets are maintained in a safe and proper manor | Responsible councillor to check on a regular basis (RA annually) that council assets such as seats, phone boxes, bus shelters, noticeboards, village signs are maintained and in good working order | Appointed councillors | Ongoing with annual risk assessment |  |
| To ensure all council policies and procedures are reviewed annually and updated as necessary | Clerk to ensure annual review process is on the agenda | Clerk and councillors | Annually in May meeting | Ongoing |

| Objective | Action | Who is responsible for action? | Timescale | Achieved? |
| --- | --- | --- | --- | --- |
| To consider planning applications in the interest of parishioners and in support of areas identified in parish plan such as maintenance of distinctive landscape, woodlands, building styles, county lanes and wide support for sensitively installed solar panels | Clerk to ensure planning applications are notified to councillors and placed on agenda. Clerk to seek time extensions from MDDC if necessary. Site visits to be arranged if required. Clerk to place on Facebook page | Clerk and councillors | Ongoing | Ongoing |
| To continue to support the Raddon Hills Group of Parishes | Two councillors to be elected as Raddon Hill representatives to attend the meetings | Councillors at annual meeting | Meetings are in February and October each year | Ongoing |
| To continue to monitor and support various groups and organisations within the parish including but not limited to: Parish Hall, Rec, Arboretum, Community Resilience Group and Boniface Trail Group | Councillors to be elected as representatives for the Parish Hall, Rec, Arboretum, CRG and Boniface Trail, Friends of the station, All councillors to support parish events where possible and maintain dialogue and visibility with village organisations | Councillors | Ongoing | Ongoing |
| To ensure continued operation of tipping rain gauge and text notification system | To take over maintenance of tipping rain gauge from 1 April 2018 - budget provision required | Appointed Councillor | From 1 April 2018 now 1 April 2019 | Ongoing |
| To continue to develop links with, and work with, Devon County Highways, including Footpaths, Devon and Cornwall Police and Mid Devon District Council including planning | Maintain dialogue and respond promptly to any communications Ensure district and county councillors are kept informed of any problems | Councillors and clerk | Ongoing | Ongoing |
| Parish Hall Car Park | To work with the Parish Hall committee to ensure that the car park remains in good repair (RA annually) and to continue to accrue funds annually towards the cost of tarmacking – Ensure each years budget includes provision | Appointed Parish Hall Councillor, Chairman and Parish Hall Committee | Ongoing with annual risk assessment | Ongoing |
| To ensure the action plan is reviewed annually | Clerk to ensure review at the annual parish meeting in May (Action plan to run May to April from May 2017) | Clerk and councillors | Annual review in May | Yearly |

| Objective | Action | Who is responsible for action? | Timescale | Achieved? |
| --- | --- | --- | --- | --- |
| To ensure continuity of nominated Community Assets | To consider re-applying for Community Asset status - current registration expires in November 2023 | Clerk and councillors | May 2023 | Yes re listed until 2023 |
| Affordable housing and future developments in the village | To ensure any future development in the parish is in line with the recommendations from the parish plans. If the old school site becomes available for development, councillors to consider housing survey requirements (from 2016 housing survey) | Councillors | Ongoing |  |
| To maintain the parish defibrillators Defib no 1 located at BT kiosk by post office and Defib no. 2 located at the Recreation Ground | To ensure that consumables (esp battery) is replaced when running low Ensure budget provision in 2018/19 | Appointed Councillor | Battery replacement due Jan 2019 for Defib no.1 and September 2020 for Defib no. 2 |  |
| To maintain Quality Council Registration and move to Quality award | The foundation level renews is April 2020 | Clerk and Councillors | July 2017 for quality award | Not eligible for Quality application. Review in 2019 |
| To continue to monitor the A377 including pollution and traffic | Review monthly pollution monitor results Develop strategic plan for A377 traffic management | Appointed Councillor | Pollution monitor – 12 month results in Feb 19 Ongoing |  |
| To identify projects for S106 contributions and notify to MDDC | Notify to MDDC | Councillors and Clerk | Ongoing |  |

Agreed:	May 2018					Date of review: During 2018