Newton St Cyres Parish Council

Action /Development Plan – Dec 2018 to April 2020

Newton St Cyres Parish Council will seek to develop, improve and maintain village services and facilities to the best of its ability within its budget and will have regard to the safety and interests of parishioners as a primary consideration in all council activities.  It will aim to represent parishioner’s views at a local, district and county level.

| Action | Implementation | Who is responsible for action? | Timescale & Review Date | Achieved? |
| --- | --- | --- | --- | --- |
| Ensure the Action Plan is reviewed annually | Clerk to ensure review at the Annual Parish Meeting. Plan to run from May to April | Clerk & Councillors | Annual review in May | Yearly |
| Implementation of Parish Plan actions | Appointed councillors to continue to work with Development Group and parish organisations to implement actions and to ensure development of future Parish Plans | Councillors and Development Group | End of April 2019 | Yes |
| Ensure continued compliance with the relevant current legislation and to promote openness, transparency and community engagement through the use of various communication media. | Clerk to ensure compliance is maintained through website and Facebook page. Councillors to maintain monthly surgeries, Annual report and Directory and two newsletters per year to be produced. Ensure budget includes provision for printing costs | Clerk and councillors | Feb & Oct |  |
| Ensure that all council assets are maintained in a safe and proper manor | Responsible councillor to check on a regular basis that council assets such as seats, phone boxes, bus shelters, noticeboards, village signs are maintained and in good working order and to ensure annual Risk Assessment | Appointed councillors | Annual review in May |  |
| Ensure all council policies and procedures are reviewed annually and updated as necessary | Clerk to ensure annual review process is on the agenda | Clerk and councillors | Annually in May meeting | Ongoing |
| Maintain Quality Council Registration and move to Quality award | The foundation level renews in April 2020 | Clerk and Councillors |  | Review in May 2019 |
| Action | Implementation | Who is responsible for action? | Timescale & Review Date | Achieved? |
| Consider planning applications in the interest of parishioners and in support of areas identified in parish plan such as maintenance of distinctive landscape, woodlands, building styles, county lanes and wide support for sensitively installed solar panels | Clerk to ensure planning applications are notified to councillors and placed on agenda. Clerk to seek time extensions from MDDC if necessary. Site visits to be arranged if required. Clerk to place on Facebook page | Clerk and councillors | Monthly | Ongoing |
| Set up new graveyard | To develop rules, regulations, agree fees etc & to agree handover with the Church | Councillors and Clerk | End of April 2019 |  |
| Continue to develop links with, and work with, Devon County Highways, including Footpaths, Devon and Cornwall Police and Mid Devon District Council including planning | Maintain dialogue and respond promptly to any communications Ensure district and county councillors are kept informed of any problems | Councillors and clerk | Monthly | Ongoing |
| Affordable housing and future developments in the village | To ensure any future development in the parish is in line with the recommendations from the parish plans. If the old school site becomes available for development, councillors to consider housing survey requirements (from 2016 housing survey) | Councillors | Review annually |  |
| Take proactive action with regards to pollution and traffic on the A377 | Review monthly pollution monitor results Develop strategic plan for A377 traffic management | Appointed Councillor | Pollution monitor – 12 month results in Feb 19 Strategic Plan Report – May 2019 |  |
| Action | Implementation | Who is responsible for action? | Timescale & Review Date | Achieved? |
| Identify projects for S106 contributions and notify to MDDC | Notify to MDDC | Councillors and Clerk | Ongoing |  |
| Support the Raddon Hills Group of Parishes | Two councillors to be elected as Raddon Hill representatives to attend the meetings in addition to the Footpath Officer and to ensure feedback to the Council | Councillors at annual meeting | Meetings are in Feb & Oct each year | Ongoing |
| Investigate a footpath from the new school site to the Rec Ground | Council to make a decision on the way forward | Councillors and Clerk | Dec 2018 |  |
| Maintain and improve parish footpaths as part of Devon County Council’s (DCC) Parish Partnership Scheme (P3) | Footpath Officer to liaise with the P3 Co-ordinator based on the information provided to Council | Footpath Officer | Ongoing | Ongoing |
| Reduce dog mess in the parish | To ensure dog waste bins are maintained and emptied and to supply free poo bags. Better publicity and ensure by-laws are enforced | Clerk and councillors | Ongoing |  |
| Support various groups and organisations within the parish including but not limited to: Parish Hall, Rec, Arboretum, Community Resilience Group and Boniface Trail Group | Councillors to be elected as representatives for the Parish Hall, Rec, Arboretum, CRG and Boniface Trail, Friends of the station, All councillors to support parish events where possible and maintain dialogue and visibility with village organisations The Council to provide financial support where necessary | Councillors | Ongoing | Ongoing |
| Facilitate the provision of allotments when demanded by 6 parishioners and /or if there are sufficient allotment holders within 3 miles of parish boundary | Where the Council is responsible the allotments to remain financially viable.and kept clean and tidy so that new tenants can be attracted | Appointed Councillor and Clerk | Ongoing |  |

Agreed:	December 2018					Date of review: May 2019